## Change_Register
Column Name | Example Value
Change_ID | CHG-001
Change_Date | 2025-01-16
Change_Type | Schema Change
Data_Asset | Orders API
Change_Description | Added quantity field
Reason | Business requirement
Impact_Level | Medium
Requested_By | Product Team
Approved_By | Data Governance
Status | Approved

## Schema_Versioning
Asset | Version | Change_ID | Effective_Date
Orders API | v1.0 | Initial | 2025-01-01
Orders API | v1.1 | CHG-001 | 2025-01-16

## Impact_Analysis
Change_ID | Impacted_System | Impact_Type | Mitigation
CHG-001 | OLTP DB | Schema update | Add column
CHG-001 | Analytics | New metric | Update model

## Approval_Workflow
Change_Type | Requires_Approval_From
Schema Change | Governance + Tech
PII Change | Governance + Security
Business Rule Change | Business Owner
Performance Change | Architecture Team

## Emergency_Changes
Change_ID | Reason | Approved_By | Post_Review
CHG-URG-01 | Production fix | Tech Lead | Completed